Data Science for the Public Good

Program Planning Document

September 4, 2018

The Data Science for the Public Good (DSPG) program equips new generations of scientists with the skills they need to support data-driven decision-making at local, state, and federal levels of policy development. DSPG was developed in 2014 and has been delivered by the Social and Decision Analytics Laboratory (SDAL in the Biocomplexity Institute of Virginia Tech. The program has been located at Virginia Tech Research Center in Arlington, VA. SDAL researchers span expertise in statistics and social & behavioral sciences with a focus on the development of quantitative methods and evidence-based research to inform decision-making and evaluation.

Each summer, SDAL researchers and DSPG students team up to work on projects that focus on the interface of data analytics and social science to address real problems at the local, state, and federal levels. Features include:

- Vertically integrated research teams with dedicated undergraduate and graduate students, postdoctoral fellow and research faculty

- Teams are horizontally integrated across disciplines and include project sponsors from local, state and federal governments, as well as other community stakeholders (e.g., Cooperative Extension or local community commission and NGOs)

- Expert training in essential tools for data science, including Hadoop, R, Python, and GIS

- Professional training through development workshops and seminars

- Individualized mentorship

- Opportunity to interact with decision-makers in industry and government agencies and attend policy events on Capitol Hill and the surrounding area

- Technical report and publication opportunities

DSPG SCHEDULES

Our DSPG is an 11 week summer program, with graduate fellows participating for 11 weeks and undergraduate students participating for 10 weeks.  The graduate fellows start one week before the undergraduate students to get familiar with the projects and the computational infrastructure of SDAL. The graduate fellows play a principal role in guiding the undergraduate students.

FOR THE USDA 3-STATE PROGRAM WE MAY WANT ALL STUDENTS TO SIMPLY BE 10 WEEKS???

Planning & Preparation Schedule

| Date | Activity |
| --- | --- |
| Early December, 2017 | - Weekly meeting with DSPG leads and Sallie begin |
| Late December, 2017 | - SDAL Website is finalized. - Application Survey and documents are finalized. - Application for Fellows are open. - Announcements for fellows and undergraduates are sent out to various departmants at VT and internship announcements in various agencies and venues - exception ASA internship ad is sent out in October. |
| Jan 31, 2018 | - Applications are due |
| Feb 17, 2018 | - Documents from candidates are reviewed by DSPG leads. - First and second-tier lists are created for candidates to be interviewed - Regrets to non-interviewees - Phone/video Interviews are conducted through February |
| Mar 1, 2018 | - Ranking and final list sent to Human Resources to prepare offers with Sallie - Human Resources contacts top applicants |
| Mar 3, 2018 | - Rejection emails to interviewees - Acceptance Letter sent out (Deadline to accept – March 10) |
| Mar 17, 2018 | - Final emails to students |

Program Schedule

| Program Week | Activities |
| --- | --- |
| Wk 1 - May 21-25, 2018 --DSPG Fellows start | Complete IRB & COI Training (2 hours) Project Presentations by Faculty (1 hour) Project Team Planning with Faculty & Sponsors (1 hour) Training: System Setup and Infrastructure (2 hours) Training: Intro Git (3 hours) Training: Git Branching and Collaboration (3 hours) Training: Collaborative Lab Notebook (1.5 hours) Training: Systems Setup and Introduction (2 hours) Office hours Project & Mentorship Assignments Project Data Exploration Begin Symposium Planning |
| Wk 2 - May 29-June 1, 2018 --DSPG Students start | Project Presentations (2 hours) IRB & Ethics in Research (1 hour) Training: Computer setup, Intro to Infrastructure, BASH, intro to plotting, and loading data (3 Hours) Training: Project Setup/Workflow, rmarkdown, knitr, Git (3 hours) Training: Git Branching and Collaboration (3 hours) Workshop: Literature Search (3 hours) Brownbag: Into to the Data Science Process & Data Profiling (Schroeder, 1 hour) All Lab Intros Project and Mentorship Assignments (1 hour) Sponsor Meetings Office hours Weekly Team Project Meetings (1 hour) Mentoring (1 hour) Weekly Wrap-Up & Project Reports (2 hours) |
| Wk 3 - June 4-8, 2018, 2018 | Training: Manipulating data in R (dplyr, pipes, eda) (3 hours) Training: Tidy (tibbles, tidyr) and Relational data (3 hours) Training: Strings, factors, datetimes, regex (3 hours) Training: Relational data, Databases & SQL (3 Hours) Training: Programming "fundamentals" (vectors, functions conditionals, iteration) (3 hours) Training: Dialects of R: base, tidyverse, data.table (3 hours) Brownbag: Intro to American Community Survey Data (1 hour) Project Work Office hours Weekly Team Project Meetings (1 hour) Mentoring (1 hour) Weekly Wrap-Up & Project Reports (2 hours) |
| Wk 4 - June 11-15, 2018 | Training: Spatial data (3 hours) Training: APIs & Loading Data, Web Scraping (3 hours) Training: Communication in R (Graphic Standards, rmarkdown, graphics, markdown formats, shiny) (3 hours) Training: Data Exploration, Analysis, and Visualization (2 hours) Brownbag: Bayesian Statistics (Higdon, 1 hour) Project Work Office hours Weekly Team Project Meetings (1 hour) Mentoring (1 hour) Weekly Wrap-Up & Project Reports (2 hours) |
| Wk 5 - June 18-22, 2018 | Training: Machine Learning (3 hours) Training: Classification & Regression Trees (3 hours) Brownbag: The Federal Government & Poverty Analysis; Capital Hill Assignment (Shipp, 1 hour) Project Work Office hours Weekly Team Project Meetings (1 hour) Mentoring (1 hour) Weekly Wrap-Up & Project Reports (2 hours) |
| Wk 6 - June 25-29, 2018 --DSPG midterm presentations | Mid-Program Presentations Project Work Office hours Weekly Team Project Meetings (1 hour) Mentoring (1 hour) Weekly Wrap-Up & Project Reports (2 hours) |
| Break - Jul 2-6, 2018 |  |
| Wk 7 - Jul y9-13, 2018 | Brownbag: Factor Analysis (1 hour) Brownbag: Social and Economic Networks (1 hour) Seminar: Erin Sikorsky (Deputy Director, Strategic Futures Group National Intelligence Council) "Global Trends: Paradox of Progress" (2 hours) Project Work Office hours Weekly Team Project Meetings (1 hour) Mentoring (1 hour) Weekly Wrap-Up & Project Reports (2 hours) |
| Wk 8 - July 16-20, 2018 | Training: Text mining (1 hour) Training: Agent Based-Modeling (2 hours) Brownbag: Secure & Federated Record Linkage (Schroeder, 1 hour) Seminar: Writing for the Media/Web (1 hour) Project Work Office hours Weekly Team Project Meetings (1 hour) Mentoring (1 hour) Weekly Wrap-Up & Project Reports (2 hours) |
| Wk 9 - July 23-27, 2018 | Brownbag: Randomized Control Trials (1 hour) Project Work Office hours Weekly Team Project Meetings (1 hour) Mentoring (1 hour) Weekly Wrap-Up & Project Reports (2 hours) |
| Wk 10 - Jul y30-Aug 3, 2018 --Posters Due | Seminar: Media Training Project Work Office hours Weekly Team Project Meetings (1 hour) Mentoring (1 hour) Weekly Wrap-Up & Project Reports (2 hours) |
| Wk 11 - August 6-10, 2018 --DSPG Student Final Week --August 9th DSPG Symposium | Wrap-up Symposium |

Students

DSPG program is open to three groups of students:

- Undergraduate students (~10): The program is open to all VT undergraduate students through the Honors college. Undergraduate students need to enroll in the summer I & 2 courses specified by the Honors college, and they receive up to 12 credits. Undergraduate students are not required to possess computational or programming skills, and students from any department are encouraged to participate.

- DSPG Alumni (2-3): Previously enrolled outstanding DSPG students that are interested in taking part in the program again are given opportunity to participate with a stipend.

- DSPG fellows (4-5): Graduate students that are currently enrolled at any U.S. university can apply for our funded fellowship positions. They are selected through a competitive national search based on their quantitative, statistical, computational and programming skills. They are expected to lead, support, and guide the VT undergraduate students together with SDAL faculty and postdocs.

Faculty & postdoc responsibilities

- Propose projects and write-up descriptions (see attached examples)

- Lead projects

- Arrange interaction with project sponsors

- Faculty presence & attendance to project meetings

- Student performance monitoring and early action

- Mentorship

- Training & Brownbags

- Arrange interesting site visits and activities

Projects

DSPG involves a wide variety of projects that address real-world problems proposed by decision makers from agencies at various levels (local, federal, state), who are referred to as sponsors. The sponsors are expected to interact with the project team throughout and provide feedback. The research projects for the respective DSPG program are defined in advance through proposals by faculty and sponsors.

- Projects should be scaled to a level where a team of 2–3 students can make significant progress over 10 weeks, with good likelihood of arriving at some definitive result. Students will participate on at least 2 projects during the course of the summer program.

- Final list of projects (the lead, SDAL team, and DSPG team size), determined by SDAL Director in consultation with DSPG leads based on project scope and alignment to SDAL programmatic (funded projects and program development) priorities and skill sets of students.

- Project leads (faculty and postdocs) present the projects to the students when they arrive.

Final Project List and sponsors from DSPG 2018

| Sponsoring Agency | Project Title |
| --- | --- |
| VT Office of Academic Decision Support | New Metrics for Assessing Virginia Tech Student Success |
| National Center for Science and Engineering Statistics (NCSES), National Science Foundation (NSF) | STEM Pathways |
|  | Measuring the Scope and Impact of Open Source Software Innovation |
|  | Measuring Business Innovation Using Non-Traditional Data Sources |
| U.S. Army Research Institute for the Social and Behavioral Sciences | Community Embeddedness of Army Soldiers |
| Roanoke Valley Alleghany Regional Commission | Create Community-Scapes for City of Roanoke and Allegheny Valley Regions in Virginia |
| Virginia Cooperative Extension (VCE) | VCE Community Dashboard |
| Community Progress Network | Arlington Equity Composite Indicators |
| Arlington County Department of Human Services | DHS Data Linkage & Characterization Phase II |
| Arlington County Police Department | Alcohol-Related Crime Reduction Strategies for Restaurants and Nightlife in Arlington |
| Virginia Department of Social Services (VDSS) | Fitness of VDSS Administrative Data Sources for Household and Family Categorization |
| UMFS | Exploring Demographic and Administrative Data to Better Recruit Foster Parents and Reduce Disruptions in Foster Care |

Seminars and Brownbags

Throughout the DSPG program, SDAL researchers, external researchers, and policy makers are invited to give lectures/talks (seminars) or brief demonstrations/trainings (brownbags) on various topics. These seminars and brownbags are scheduled as they come, suggested by faculty and coordinated by the seminar chair and administrative staff.

Examples can be seen in the program schedule above such as:

- Week 7 Seminar by Erin Sikorsky, Deputy Director, Strategic Futures Group National Intelligence Council, on "Global Trends: Paradox of Progress", and

- Week 8 Brownbag by SDAL Senior Research Scientist Aaron Schroeder on Secure & Federated Record Linkage

- DSPG Symposium

The Data Science for the Public Good (DSPG) Symposium is where DSPG students and fellows present their research projects. This symposium highlights how the DSPG program equips new generations of scientists with the skills they need to develop data-driven policy and decision-making.

The DSPG program focuses at the interface of data analytics and social science to address real problems at the local, state, and federal levels of government. The Symposium includes keynote speakers followed by a poster session and networking reception.

Keynote Speakers from DSPG 2018 and 2017:

• Catherine Woteki | Former Undersecretary for Research, Education and Economics and Chief Scientist, U.S. Department of Agriculture

• Wayne Strickland | Executive Director, Roanoke Valley-Alleghany Regional Commission

• Nancy Potok, Chief Statistician of the United States, Office of Man^ment and Budget

• David Yokum, Director, The Lab @ DC, Executive Office of the Mayor, Office of the City Administrator