Fitness of VDSS Administrative Data Sources to Support Household and Family Classification

Project Sponsor: Virginia Department of Social Services

Team: Brian (PI), Aaron

Project Client: Jeff Price, Director of Research and Planning

Project Background

According to the latest figures from the U.S. Census Bureau, approximately two-thirds of American households are also classified as families. These two terms, “household” and “family”, are often used interchangeably, but the Census Bureau draws a careful distinction:

- A household consists of one or more persons living in the same house, condominium or apartment. They may or may not be related.

- A family has two or more members who live in the same home and are related by birth, marriage or adoption.

Therefore, by these definitions, all families are also households, but not all households are families.

Accurately defining households and families can be critical to making informed social service public policy decisions. Being able to accurately derive these classifications using already existing administrative records would preclude the need for additional resources to be allocated toward additional data collection activities.

Project Goal

Determine the fitness of selected VDSS administrative data record systems for accurately deriving household and family classifications. The administrative records systems to be assessed for this project are:

- The Online Automated Services Information System (OASIS); and,

- The Virginia Case Management System (VaCMS).

Project Tasks

- Problem Definition

  - work with VDSS representatives and conduct literature review to best define the issue of household and family definition in social service policy making and social science research

- Data Profiling, Preparation and Exploration

  - conduct analyses of Data Structure, Data Quality, Data Provenance and Metadata

  - conduct data cleaning, transformation and restructuring as required

  - create assessment of data source fitness for supporting the accurate definition of households and families

- Data Discovery

  - conduct process of discovery, as necessary, of additional data sources that, when used in conjunction with OASIS and/or VaCMS data may support a more accurate definition of households and families.

- Metric Creation and Validation

  - create and assess the accuracy and potential utility of new household and family definitions supported by the OASIS and VaCMS (and potentially other) data systems.

Projected Time: 10 weeks