# 2018 DSPG Project Plan – DHS Record Linkage

(Weeks 1-2) Background readings: Students will read the original Fellegi-Sunter paper to understand the fundamentals of probabilistic data linkage. Aaron has an excellent high-level write up.

Deliverables: The fellow assigned to the project will prepare a 10 minute presentation illustrating the basic ideas.

(Weeks 2-4) Deterministic Linkage: The Fellegi and Sunter model has issues integrating data elements which are often missing, such as social security numbers. When the SSN exists and matches it should provide a strong positive weight, but when it is missing it should provide no evidence. As it is, a missing SSN counts as a strong negative weight, which is inappropriate. This can be resolved by pre-linking records in a deterministic way. Students will develop methodology to pre-link records based on deterministic rules and then pass the pre-linked sections to a probabilistic linker.

Deliverables: A deterministic/probabilistic linkage algorithm. The code will be well documented and ready for integration in current systems.

(Weeks 3-7) Geocoding: Geocoding addresses is currently done using Google’s streetview API, which is a data privacy concern for the DHS. This step is necessary because it allows to extract addresses in a unified format. Students will explore methods for harmonizing address records in such a way that does not require external resources.

Deliverables: Either an open source geocoding technique which does not rely on passing addresses to a third party, or if none exists, a document detailing the options explored.

(Weeks 8-10) Data source expansion: There are many data sources which are currently not being linked. Students will generalize the methods already developed to other data streams relevant to the DHS.

Deliverables: After the methods described above are in place, the students will develop the idiosyncratic data cleaning code to integrate at least one of the other data sources used by the DHS. They will also document the steps required for this process in sufficient detail to allow us to integrate additional sources after the program has ended.

(Weeks 8-10) Linkage method comparison and basic predictive modeling: To assess the results of the data linkage process, students will compute summaries and simple predictive models using the raw data, the data deduplicated by the DHS’s old methods, and the data deduplicated by our method.

Deliverables: (1) Basic summaries of service utilization by time and space, to whatever resolution is possible, under the different data linkage regimes. (2) Basic statistical models of the predictors of service utilization under the different data linkage regimes.