# 2018 DSPG Project Plan – NCSES Innovation

(Week 1) Preliminary screening: As the program progresses, there will be an all-hands effort to manually read and label ProQuest articles concerning pharmaceutical devices. Of primary import are data concerning new products, such whether or not they’re mentioned and what their names are. We will also track other features relating to the products, as well as other data elements that could be used as features in a classifier. Once we have a fellow on the project, project leadership will parse a few articles and create a table of things to hunt down throughout the program.

Deliverables: A spreadsheet with columns for all the data elements the students will extract throughout the program

(Weeks 1-10) Manual article labelling: As the program progresses, students will continuously read articles and extract the data elements determined to be relevant in the first week’s screening. This work will proceed in parallel with the other tasks for this project, as the models to be used with this data can be developed before all the data are parsed.

Deliverables: A growing collection of parsed articles for use in predictive modeling.

(Weeks 1-10) Feature Creation and Extraction: Crucial to the success of a predictive model are the right features for use in prediction. As we explore the articles, we will discover patterns in the articles which can discriminate articles which mention new products from those which do not. Some features will need to be extracted, but some we will be able to compute.

Deliverables: A growing list of features to include in our classifier.

(Weeks 2-4) Data cleaning and Preparation: The ProQuest data has been parsed from the raw html, but still needs more work to be in an optimal form. Students will develop code to load in article sets into corpus objects, perform cleaning and stemming, deduplicate articles, and otherwise prepare the data for use in text mining software.

Deliverables: Cleaned, deduplicated corpus objects, as well as the code used to make those transformations.

(Weeks 4-9) Model Development: Students will explore different classifiers and see which have desirable performance profiles. Models will be assessed on their running time as well as out-of-sample predictive accuracy. Topic modeling techniques such as latent Dirichlet allocation will also be explored. Students will also run the models trained on pharmaceutical data on articles from other NAICS codes to assess generalizability.

Deliverables: (1) A classifier to determine which articles are about product innovation.

(Weeks 8-10) Analysis of New Produts: The goal of the above development is to extract articles which mention new products so as to count the entry of new products into the market. Once we have identified which articles mention new products, and what those products are, the students will prepare tabulations of these new articles.

Deliverables: (1) A report detailing how many new products have entered the market.