Exploring Demographic and Administrative Data to Better Recruit Foster Parents and Reduce Disruptions in Foster Care (UMFS Study)

Project Lead: Brian J. Goode, Research Scientist SDAL

Project Team:

- Josh Goldstein, Research Scientist SDAL

- 1 Graduate Fellow, DSPG/SDAL

- 2-3 Undergraduate Students, DSPG/SDAL

Project Sponsor: United Methodist Foster Services (UMFS)

Project Contact: Nancy Campos, Evaluation Specialist

Project Background:

- Disruptions in foster care occur when a foster care arrangement is ended before a permanent home is established for a foster child.

- Disruptions cause additional stresses to the foster child and family.

- Identifying candidate families that match to UMFS core values and targeting recruitment to participate as foster families can potentially reduce disruptions in foster care.

Project Goals

- Conduct an exploratory study around the demographics of current foster families; identify relevant groupings in the data

- Identify groups that map best to UMFS core values.

- Explore additional data sources to help target recruitment efforts more effectively to reach out to candidate foster families.

Project Tasks

A.) Problem Definition

- Work with UMFS representatives and relevant literature in the field to identify the problem of disruptions in terms of foster family characteristics

- Posit relationships between between available data sources and UMFS core values.

B.) Data Profiling, Preparation and Exploration

- Clean data, and conduct initial exploration and analyses

- Using theoretical and data driven techniques, develop models for indicators of families mapping to UMFS core values.

C.) Data Discovery

- Explore additional data sources related to recruitment variables of foster families.

- Performed on an as-needed basis.

D.) Metric Creation and Validation

- Conduct a validation study over two samples drawn from the UMFS demographic dataset.

Projected Time: 10 weeks