Data Science for the Public Good

Army Research Institute – Discovering the Potential and Use of New Data Sources to Measure the Soldier’s Social Determinants of Health in the Context of Community Embeddedness

Project sponsor

- Kelly S. Ervin, Ph.D., Senior Research Psychologist, U.S. Army Research Institute (ARI), Ft. Belvoir, VA

- June 14 meeting, tentative, otherwise will reschedule for another day

Proposed SDAD team

- Stephanie Shipp, DSPG project lead, economist

- Vicki Lancaster, statistician

- Josh Goldstein, statistician

- Nat Ratcliff, social psychologist

- Joel Thurston, social psychologist

- 1 Graduate Students with R skills and interest in health or education.

- 2-3 undergraduate students with R skills and interest in health or education.

Project description

- Project summary.

  - SDAD overall project: Within the U.S. Army, there is increasing interest in understanding how physical, cognitive, and social behaviors drive Soldiers to successfully meet the challenges of a world in persistent conflict. SDAD is examining the social component of Soldier performance by assessing constructs that can affect performance such as adaptability, motivational traits, empathy, and commitment to Army Values and the Warrior Ethos. SDAD is conducting research to define and quantify the social behaviors of Soldiers by identifying constructs that capture Soldier, team, and unit performance. We are interested in exploring data sources that have potential to inform this research with a focus on community embeddedness.

  - DPSG project: This project grows our inventory of data for ARI and SDAD research projects. It directly contributes to deliverables for our ARI project and expands our health and education portfolio by defining Soldiers’ health to include the social determinants of health and education, with a focus on community embeddedness. The question to be answered is whether these data sources are useful for ARI research.

- Project scope. Using the SDAD Data Science Framework as a guide, the research will focus on: (1) discovering, inventorying, screening, profiling and documenting the data sources, including accessibility, resulting in a technical report (common outline across projects to be provided); (2)  acquiring data available on the web (for BRFSS for Virginia and for DoDEA for all schools and areas); (3) reviewing and documenting the literature for examples of uses of these data sources and developing a crisp research question for constructing composite indicator(s); (4) using the research question as a guide for each data source to conduct exploratory data analysis; and (5) describing and presenting the indicators.

Building on a broader DSPG ARI project in 2018, the first step will be to discover data sources that have the potential to address questions about a Soldiers’ behavior. Three data sources of initial interest are the

- Centers for Disease Control and Prevention (CDC) Behavioral Risk Factor Surveillance System (BRFSS) https://www.cdc.gov/brfss/index.html data provide insights regarding health-related risk behaviors, chronic health conditions, and use of preventive services in communities near Army installations;

- Department of Defense Education Activity (DoDEA) Data Center (https://www.dodea.edu/ and https://www.dodea.edu/datacenter/ contains links to Student Achievement data, enrollment figures, School Report Cards, and more;

Each student will choose one source to discover, document, acquire, and explore the data for their potential to understand Soldiers’ behavior and community embeddedness, guided by a research question.

- Importance to sponsor. Measuring the social component of Soldier performance will require novel data sources to capture performance characteristics such as adaptability, motivational traits, empathy, and commitment to Army Values and the Warrior Ethos.

- Importance to SDAD. SDAD is interested in expanding its use of data sources to inform ARI research. The two data sources provided in this project description are large and have multiple components, thus providing students with the experience of implementing the Data Science Framework steps through exploring the data to creating indicators.

- Prior work. We will share and present the ARI2 annual report and present findings from recent presentations, e.g. Administrative Data Research Facilities (ADRF) and Military Operations Research (MORS) conferences.

- Student involvement. Students will: (1) discuss the ethical implication of the research starting with a review of the ARI project IRB protocol, project goals, and other relevant materials; (2) conduct a literature review to identify how data are used and to formulate a crisp research question(s) on a topic related to community embeddedness; (3) use the Data Science Framework to conduct data discovery of possible data sources and then to discover the availability and usefulness the above two multi-component data sources that could provide insights about Soldier performance and behavior; (5) profile selected variables and conduct exploratory data analysis to address the research question(s); (6) prepare a Sage Brief for each data source; and (7) review and summarize ethical insights and conclusions. See attached timeline for complete set of activities.

- Request for students. The project requests 1 graduate students and 2-3 undergraduate students. Ideal students are skilled R users with a social science or policy background, interested in research in one or more of the following topics - the military, risky health behaviors, education, and prior experience using administrative and survey data.

Expectations.

The project will deliver for each data source: 1) data discovery of multi-component data sources that provide insights about Soldier performance and behavior; 2) selection of a large, multi-component source of data to investigate; 3) data acquisition, profiling,  and exploration to address a research question focused on community embeddedness; 4) Sage briefs for online publication (https://www.methodspace.com/qual-data-analysis-narrative-research/); and 5) ARI symposium posters and presentations.

Timeline for DSPG Army Research Institute (ARI) – Data Discovery of All Possible Sources of Data to Inform Soldier Behavior

.

|  |  |  |  | DSPG 2019 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 |
| PHASE |  |  | TASKS | 5/28 - 5/31 | 6/3 - 6/7 | 6/10- 6/14 | 6/17 - 6/21 | 6/24 - 6/28 | 7/1 - 7/5 | 7/8 - 7/12 | 7/15 - 7/19 | 7/22 - 7/26 | 7/29 - 8/2 | 8/5 - 8/9 |
| Training | Ethics |  | Complete IRB, RCR, and COI trainings. |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Complete/review ARI project ethics checklist. |  |  |  |  |  |  |  |  |  |  |  |
|  | Skills |  | Complete tidyverse and data wrangling courses |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Complete other DSPG courses, |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Complete git courses. |  |  |  |  |  |  |  |  |  |  |  |
|  | Workflow |  | Review documentation standards. |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Review collaboration tools – SDAD wiki. |  |  |  |  |  |  |  |  |  |  |  |
| Data Science Framework | Discovery |  | Overall data discovery and then discover multi-component sources of data, BRFSS and DoDEA |  |  |  |  |  |  |  |  |  |  |  |
|  | Inventory |  | Create questions & template to assess usefulness of these data sources for ARI research |  |  |  |  |  |  |  |  |  |  |  |
|  | Screen |  | Review documentation for BRFSS, DoDEA |  |  |  |  |  |  |  |  |  |  |  |
|  | Document |  | Describe data sources and relevancy to ARI |  |  |  |  |  |  |  |  |  |  |  |
|  | Acquire |  | Acquire, profile, and conduct exploratory data analysis for selected source of data to study. e.g. Download BRFSS data for Virginia, and DoDEA data for all schools |  |  |  |  |  |  |  |  |  |  |  |
| Literature | Read |  | Read relevant literature on uses of data sources and how they could be used to inform Soldier behavior to formulate research question(s) for each data source focused on community embeddedness. |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Integrate literature review into Sage briefs (draft). |  |  |  |  |  |  |  |  |  |  |  |
| Use Cases | Profile |  | Select and profile relevant variables |  |  |  |  |  |  |  |  |  |  |  |
|  | Clean |  | Clean variables as needed for research. |  |  |  |  |  |  |  |  |  |  |  |
|  | Integrate |  | Prepare data for analysis. |  |  |  |  |  |  |  |  |  |  |  |
|  | Explore |  | Conduct exploratory data analysis Visualize and analyze data in context of research question(s) |  |  |  |  |  |  |  |  |  |  |  |
| Analysis |  |  | Prepare summaries of use cases |  |  |  |  |  |  |  |  |  |  |  |
| Communication | Stakeholder |  | Meet with stakeholder. |  |  |  |  |  |  |  |  |  |  |  |
|  | Poster |  | Complete symposium poster(s). |  |  |  |  |  |  |  |  |  |  |  |
|  | Brief |  | Draft and prepare publication-ready Sage brief(s). |  |  |  |  |  |  |  |  |  |  |  |