DSPG Project Proposal

Machine Learning Techniques to Measure Business Innovation

Project Sponsor:

National Science Foundation, National Center for Science and Engineering Statistics

Gary Anderson, Senior Science Resources Analyst

Proposed SDAD Team:

- Devika Nair, Research Scientist

- Gizem Korkmaz, Research Associate Professor

- 1 graduate fellow

- 2 undergraduate fellows

Goal:

This project aims to test the feasibility to identify, measure, and characterize product innovation using non-survey data sources.

Description:

Our hope is to develop methods to complement and enhance the NSF-administered BRDIS survey that collects information from a representative set of companies and asks whether they have introduced a new product to the market. Specifically, we are developing text-based methods to be applied to administrative (e.g., financial filings) and opportunity data (e.g., trade journals, press releases) to determine:

- whether a company has launched a new product?

- how many new products are introduced?

- what are the features of the new product(s)?

- how that innovation trends over time?

To answer these questions, we measure innovation in terms of products, and seek to capture a new product and characterize its trajectory across a number of text based sources. Additionally, we focus on the pharmaceutical and medical device industry that are highly regulated such that new products require approval from the Food and Drug Administration (FDA). We make the assumption that the FDA approval dataset (which is publicly available) is the universal set of all new products, and ask what the portion of these products we can capture using administrative and opportunity data.

We chose to focus on the pharmaceutical and medical device industry because of the strictly regulated process of launching new products that is specific to this industry. Consider the following as a high-level illustration of the process a new drug or medical device might take to the market:

- Research & Development: Company undertakes research to develop, test, and trial new device and drug.

- FDA Application: Company submits application to FDA for device or drug approval.

- Approval Announcements: FDA releases announcements to the public.

- Press Activity: Media outlets report on the announcements, company and competitor relationships, and launches to market. [FOCUS]

- Market Activity: Company retails device or drug.

- Financial Reports: Company submits financial reports to US Securities & Exchange Commission (SEC).

By tracing products through their lifecycle from FDA approval through financial impact, we can expand upon the BRDIS survey results by providing additional context and information around what innovation looks like in the pharmaceutical industry. Furthermore, we can illustrate a process by which innovation can be uncovered and measured, at least in a highly regulated environment.

Phases:

- Training

- Literature Review?

- Data Discovery – minimal

  - Market data sources

  - Name matching between chemical names and brand names

- Data Ingestion

- Data Cleaning

- Machine Learning Models

- Model Validation

SDAD Data Assets:

- SEC 10-K Filings, 2013-2016

- FDA Approvals, 2013-2016

- Dow Jones Factiva, articles based on query [FOCUS]

  - Labeled set of articles

Deliverables:

- Literature Review

- Method for identifying and characterizing new products

  - at minimum - pharmaceutical industry

  - ideally – flexible enough to carry into other industries

- Cleaned datasets of new products (and their features and sources)

  - At minimum – from existing SDAD data assets

  - Ideally – from novel data sources

- Machine Learning Output – range of possible outcomes

  - Modeled relationships

  - Map networks

- Visualization

Timeline for DSPG Fairfax CommunityScape creation.

|  |  |  | DSPG 2019 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 |
| PHASE |  | TASKS | 5/28 - 5/31 | 6/3 - 6/7 | 6/10- 6/14 | 6/17 - 6/21 | 6/24 - 6/28 | 7/1 - 7/5 | 7/8 - 7/12 | 7/15 - 7/19 | 7/22 - 7/26 | 7/29 - 8/2 | 8/5 - 8/9 |
| Training | Ethics | Complete IRB, RCR, and COI trainings. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete/review project ethics checklist. |  |  |  |  |  |  |  |  |  |  |  |
|  | Skills | Complete tidyverse and data wrangling courses if needed. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete working with Census data courses if needed. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete spatial data courses if needed. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete git courses if needed. |  |  |  |  |  |  |  |  |  |  |  |
|  | Workflow | Review documentation standards. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Review collaboration tools. |  |  |  |  |  |  |  |  |  |  |  |
| Literature | Read | Read relevant literature on social determinants of health. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Read relevant literature on maternal obesity and child outcomes. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Read relevant literature on vulnerability indexes. |  |  |  |  |  |  |  |  |  |  |  |
|  | Integrate | Produce social determinants of health annotated bibliography. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Produce maternal obesity child outcomes annotated bibliography. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Produce vulnerability index annotated bibliography. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Integrate literature reviews into Russell Sage brief(s) (draft). |  |  |  |  |  |  |  |  |  |  |  |
| Analysis | Discovery | Assess potential location-based data sources. |  |  |  |  |  |  |  |  |  |  |  |
|  | Processing | Construct synthetic data-based vulnerability index. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Acquire, clean, and link location-based data. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Clean Inova data and place cohort in context. |  |  |  |  |  |  |  |  |  |  |  |
| Communication | Stakeholder | Meet with stakeholder. |  |  |  |  |  |  |  |  |  |  |  |
|  | Poster | Complete symposium poster(s). |  |  |  |  |  |  |  |  |  |  |  |
|  | Brief | Publication-ready Russell Sage brief(s). |  |  |  |  |  |  |  |  |  |  |  |