DSPG

Validation of Broadband Data and Identification of Factors that Predict Property Values

Project Sponsor:

John Pender, Senior Economist, USDA Economic Research Service (ERS)

Proposed SDAL Team:

Josh, Teja, Devika, Stephanie

Project Summary:

USDA Economic Research Service is interested in understanding the impact of broadband development on rural prosperity. As part of a larger project, the DSPG team will address the following questions.

- Can we validate the data that is collected by the FCC on broadband availability and subscription rates?

- Based on a review of the literature, what factors are relevant for the prediction of property values?

Project Description:

USDA would like to know whether broadband development has an effect on rural prosperity, as measured by changes in property values and quality of life indicators in rural communities. One part of the project will look at the effects of programs that develop broadband infrastructure, with a focus on grants and loans from the USDA Rural Utility Service (RUS).

To measure the availability of broadband, the Federal Communications Commission (FCC) collects information from broadband providers twice a year (Form 477), including a list of available providers by census block and subscription rate by census tract geographies. There are issues with the FCC published estimates – they use only the advertised speeds, and a single residence per census block is enough to list a provider as available over the entire block. The summer project will attempt to identify where FCC measurements are unreliable in the US using supplementary data on broadband availability, including data from BroadbandNow.com, and the 2013-2017 5-year American Community Survey estimates. Students will do an exploratory comparison of these data sources and develop heuristics for measuring the fitness-for-use of FCC data, and assess when it is appropriate to remove, replace, or adjust the FCC estimates.

As a second piece of the project, students will conduct a literature review of factors other than broadband that shape property values. This review will inform subsequent property value modeling done outside of DSPG.

Both of these tasks directly support the division’s larger ERS project.

Articles and summaries for background reading on FCC data quality will be provided during Week 1. FCC and ACS datasets will be provided to the students, and they will acquire data from BroadbandNow.com. Students will be expected to do exploratory data analysis on these three (and potentially other) broadband datasets, with the goal of measuring discrepancies in measurements and rules for correcting e.g. the systematic overestimates of availability in the FCC data. They will also conduct a literature review looking at existing studies measuring property value as a response, and conduct an accompanying data discovery exercise of housing data.

The team will require 2-3 undergraduate students and 1 graduate student. Students should have experience with R.

Expectations/Deliverables:

- Data discovery: Are there additional data sources to measure broadband deployment?

- Comparison and validation of Federal Communications Commission (FCC), American Community Survey (ACS), BroadbandNow.com, and additional data sources discovered:  Students will undertake cleaning, transforming, exploratory data analysis, and development of heuristics for using FCC broadband data.

- Annotated bibliography and narrative review of factors predicting property values.

- Sage brief for online publication.

- Symposium poster and presentation.

|  |  |  | DSPG 2019 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 |
| PHASE |  | TASKS | 5/28 - 5/31 | 6/3 - 6/7 | 6/10- 6/14 | 6/17 - 6/21 | 6/24 - 6/28 | 7/1 - 7/5 | 7/8 - 7/12 | 7/15 - 7/19 | 7/22 - 7/26 | 7/29 - 8/2 | 8/5 - 8/9 |
| Training | Ethics | Complete IRB, RCR, and COI trainings. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete/review project ethics checklist. |  |  |  |  |  |  |  |  |  |  |  |
|  | Skills | Complete tidyverse and data wrangling courses if needed. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete working with Census data courses if needed. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete spatial data courses if needed. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete git courses if needed. |  |  |  |  |  |  |  |  |  |  |  |
|  | Workflow | Review documentation standards. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Review collaboration tools. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Meet with John Pender, sponsor |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Meet with Chris Ali, UVA BB expert |  |  |  |  |  |  |  |  |  |  |  |
| Literature | Read | Read relevant literature on broadband data quality. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Read relevant literature on property values. |  |  |  |  |  |  |  |  |  |  |  |
|  | Integrate | Produce key property value factors annotated bibliography. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Integrate literature review into Russell Sage brief(s) (draft). |  |  |  |  |  |  |  |  |  |  |  |
| Data | Discovery | Brainstorm additional broadband datasets. |  |  |  |  |  |  |  |  |  |  |  |
|  | Access | Acquire BroadbandNow.com and other data. |  |  |  |  |  |  |  |  |  |  |  |
|  | Processing | Clean data. |  |  |  |  |  |  |  |  |  |  |  |
| Analysis |  | Exploratory comparison of broadband data sources. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Developing heuristics for using FCC data. |  |  |  |  |  |  |  |  |  |  |  |
| Communication | Stakeholder | Meet with John Pender, sponsor |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Meet with Chris Ali, UVA broadband expert |  |  |  |  |  |  |  |  |  |  |  |
|  | Poster | Complete symposium poster(s). |  |  |  |  |  |  |  |  |  |  |  |
|  | Brief | Publication-ready Sage brief(s). |  |  |  |  |  |  |  |  |  |  |  |