Building a Fairfax County CommunityScape to Understand Social Determinants of Health and Prosperity

Project sponsors

- Michelle Gregory, Office of Strategy Management, Fairfax County Health and Human Services

- Sophia Dutton, Office of Strategy Management, Fairfax County Health and Human Services

- Kathi Huddleston, Director of Clinical Research Projects, Inova Translational Medicine Institute

- Sahel Hazrati, Lead Epidemiologist/Biostatistician, Inova Translational Medicine Institute

- Grace Lawrence, Director of Research Projects, Inova Translational Medicine Institute

Proposed SDAD team

- Teja Pristavec: DSPG project lead

- Stephanie Shipp: Fairfax project component lead

- Joy Tobin: Inova project component lead

- Vicki Lancaster: project support

- Josh Goldstein: project support

- Nat Ratcliff: project support

- Devika Nair: project support

Project description

  - Project summary. This project will build Fairfax County CommunityScapes using diverse sources to contextualize where citizens live, learn, work and play. The  CommunityScapes will be a collection of composite indices that will provide the foundation for quantitative characterization of the county’s social determinants of health and wealth. The team will develop composite indices using synthetic data techniques based on local, state, and federal data sources, and input from project sponsors.

- Larger SDAD projects. Building Fairfax County CommunityScapes supports two ongoing SDAD projects:

  - Maximizing the Use of Existing Data for Policy and Planning by Creating Indices for Predictive and Prescriptive Analytics. Developing multiple composite indicators to measure vulnerability and other social determinants of health characteristics that are of interest to both the Fairfax County and Inova sponsors (e.g., health and economic equity).

  - Fusing Data Science and Maternal Obesity in Northern Virginia: Maternal Health and Early Childhood Health Outcomes project. Developing Fairfax CommunityScapes will allow us to subsequently place the Inova First 1,000 Days of Life and Beyond study cohort in socioeconomic and environmental context, providing a better understanding of factors that shape health outcomes in the Inova cohort.

- Project scope. The project will focus on 1) reviewing social determinants of health and wealth literature; 2) reviewing composite index construction literature; 3) data discovery, screening, acquisition, fitness-for-use assessment, preparation, linkage, and exploration; 4) constructing composite indices based on selected data and stakeholder input for sub-county areas of Fairfax County (e.g., school attendance areas, political districts, opportunity zones) along with variability measures; 5) data visualization and interpretation.

- Importance to sponsor. This project will allow the Inova sponsor to better understand the First 1,000 Days of Life and Beyond study cohort, its representativeness vis-à-vis a CommunityScape that captures the social determinants of health factors beyond traditional demographic features captured in the study that contribute to maternal and child health outcomes. It will allow the Fairfax sponsor to identify the characteristics of equity and health disparities across the county and of where vulnerable populations live. These insights for both sponsors can help influence policy and program development at the neighborhood, school, or political district boundaries. The CommunityScapes will establish a baseline for measuring future change for new policies and practices across the county.

- Importance to SDAD. This project grows our inventory of Virginia-specific data, furthers our work on indicator construction, directly contributes to deliverables for two existing projects, strengthens our relationship with Fairfax County as an existing sponsor. Further, it develops our partnership with Inova as a new collaborator in the healthcare area that could lead to future joint research.

- Prior work. This project builds on our collaborations with Fairfax County and Arlington County. We will provide students with materials from these partnerships, and use the SDAD Roanoke Valley and Alleghany Region project as a finished product example.

- Student involvement. Students will 1) select 1-2 focal indices relevant to sponsors; 2) review literature on social determinants of health and composite index construction; 3) continually discuss the ethical implication of the research starting with a review of the Fairfax project IRB protocol, project goals, and other relevant materials; 4) conduct data discovery, screening, acquisition, fitness-for-use assessment, preparation, linkage, and exploration; 5) construct composite indices, informed by existing research, statistical methods, and stakeholder input; 6) visualize and interpret their work.

- Request for students. The project requests 2 graduate students and 2 undergraduate students. Ideal students are organized and skilled R users with a social science or statistics background, health and policy focus, and prior experience using spatial data.

Expectations

The project will deliver 1) annotated bibliographies on social determinants of health and wealth and on related composite indices; 2) two briefs for consideration by SAGE for online publication; 3) Fairfax County CommunityScape symposium poster(s) and presentation(s).

Timeline for DSPG Fairfax CommunityScape creation.

|  |  |  | DSPG 2019 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 |
| PHASE |  | TASKS | 5/28 - 5/31 | 6/3 - 6/7 | 6/10 - 6/14 | 6/17 - 6/21 | 6/24 - 6/28 | 7/1 - 7/5 | 7/8 - 7/12 | 7/15 - 7/19 | 7/22 - 7/26 | 7/29 - 8/2 | 8/5 - 8/9 |
| Training | Ethics | Complete IRB, RCR, and COI trainings. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete/review project ethics checklist. |  |  |  |  |  |  |  |  |  |  |  |
|  | Skills | Complete tidyverse and data wrangling courses if needed. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete working with Census data courses if needed. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete spatial data courses if needed. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete git courses if needed. |  |  |  |  |  |  |  |  |  |  |  |
|  | Workflow | Review documentation standards. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Review collaboration tools. |  |  |  |  |  |  |  |  |  |  |  |
| Literature | Read | Read relevant literature on social determinants of health. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Read relevant literature on composite indices. |  |  |  |  |  |  |  |  |  |  |  |
|  | Integrate | Produce social determinants of health annotated bibliography. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Produce composite index annotated bibliography. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Integrate literature reviews into Russell Sage briefs (draft). |  |  |  |  |  |  |  |  |  |  |  |
| Data | Discovery | Conduct data discovery and screening. |  |  |  |  |  |  |  |  |  |  |  |
|  | Processing | Acquire, clean, and otherwise prepare data. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Join and explore data. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Develop composite indices. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Visualize and interpret findings. |  |  |  |  |  |  |  |  |  |  |  |
| Communication | Stakeholder | Meet with stakeholder. |  |  |  |  |  |  |  |  |  |  |  |
|  | Poster | Complete symposium poster(s). |  |  |  |  |  |  |  |  |  |  |  |
|  | Brief | Publication-ready Sage brief(s). |  |  |  |  |  |  |  |  |  |  |  |