Returning Citizens Reentry Program

- Project Sponsor/Collaborator: Initiator: Gregory Fairchild, Darden GSBA; Other sponsors: Virginia Department of Corrections (VADOC): Tama Celi, Libbie Miller, Yan Jin

- Proposed DSPG Team: Nathaniel Ratcliff, Joel Thurston, Bayoan, Gizem Korkmaz, Aaron Schroder, Joel Thurston

- Project Summary: What are the summative impacts of education during incarceration? In addition to potential lowered recidivism, what are other benefits? How does the existing collaborative program between Resilience Education and the Virginia Department of Corrections deliver against these potential benefits?

  - This project isn’t a part of another SDAD initiative;

  - The project scope includes the following – (a) augment existing research on the impact of the Resilience Education initiative; (b) evaluate the pre- and post-release impact of education during incarceration; (c) utilize available existing data from Virginia Department of Corrections; (d) collect new data to capture potential non-measured impacts; and (e) interview key stakeholders, agencies and individuals.

- Motivation: Education during incarceration is not widespread and its delivery against purported benefits is not well understood or carefully examined. This project will help determine efficacy and perhaps lead to diffusion of other initiatives with similar goals.

- Prior Work: In January 2019, Virginia DOC reviewed Resilience Education program with a primary focus on recidivism. There is an existing report and perhaps an available dataset.

- Anticipated Work: The anticipated scope of the project includes the following – (a) literature review: conduct literature review to synthesize the research literature on education while incarcerated and to identify potential gaps in past research; (b) research questions: develop research questions and hypotheses that can inform research and policy on education programs in prisons, and specifically, the education program being conducted by Darden; (c) data discovery: identify pre-existing data sources or data collection opportunities (Plan A: utilize existing data from Virginia DOC, parole officers, and other metrics collected from the Darden education program; Plan B: utilize publicly-available data sources of education programs in prisons from state and federal agencies like the Department of Justice; Plan C: examine what institutions have education programs across the U.S., examining factors like location, public versus private ownership, and crime data of surrounding areas); (d) data analysis: organize and analyze available data sources; and (e) memorandum of recommendations: compiling the research literature and utilizing available data, the team would provide recommendations on how to evaluate the Darden education program including how to design a study to assess the program (e.g., random control trials) and the impacts of the program on those who participate (e.g., proximal outcomes: positive/negative affect, motivation, perceptions of committing crime, development of concrete skills, number of in-prison infractions; distal outcomes: recidivism, employment status, additional education sought after prison, return on investment).

- Student special needs or skills: None. Empathy, if any.

- Minimum number of students: As anticipated by DSPG team leadership.

- Deliverables. Literature review, recommendation memo, creation of database (or recommendations on how to create one), presentation of findings, suggested next steps.