Data Science for the Public Good

NSF National Center for Science and Engineering Statistics (NCSES): Measuring the Public Funding of R&D Projects – a pilot study

Project sponsor

- John Jankowski, Ph.D., NSF, National Center for Science and Engineering Sciences, Research & Development Statistics Division

Proposed SDAD team

- Stephanie Shipp, DSPG project lead

- Graduate student with R skills and interest in measuring public R&D.

- 2-3 undergraduate students with R skills and interest in measuring public R&D.

Project description

- Project summary.

  - SDAD overall project: This is one of four NCSES projects to assess the feasibility of enhancing or supplementing NCSES survey data with publicly available administrative data.  NCSES would like to use non-survey data to measure STEM technical workforce, business innovation, free innovation, and research & development, with an initial focus on public R&D. This project focuses on the last project.

  - DPSG project: The sponsor is a member of the OECD Working Party of National Experts on Science and Technology (NESTI).  NESTI is interested in a proof of concept for an international micro database on public funding of R&D projects drawing on the increasing openness and availability of administrative microdata.

  - Using publicly available databases at federal science agencies, we will conduct a pilot study to discover, acquire, and collect data about R&D expenditures. The goal is to acquire federal grant websites to characterize government funding currently and over time.  Examples of databases to be acquired and linked are:

    - NIH RePORTER - https://projectreporter.nih.gov/reporter.cfm and https://exporter.nih.gov/

    - NSF Fastlane - https://www.nsf.gov/awardsearch/simpleSearchResult?queryText=Diran+Apelian&ActiveAwards=true  and https://www.nsf.gov/awardsearch/download.jsp

    - USDA – must access by agency, e.g., NIFA Current Research Information System  - https://cris.nifa.usda.gov/

    - EPA - https://yosemite.epa.gov/oarm/igms_egf.nsf/HomePage?ReadForm

    - Others, e.g. DOD, DOE, NASA….

- Project scope. Using the SDAD Data Science Framework as a guide, the research will focus on (1) discovering, inventorying, screening, and documenting availability of publicly available R&D expenditure data sources from federal science agencies (2)  acquiring data available on the web or directly from agency, (3) comparing the data to published estimates, accounting for different time periods (https://www.nsf.gov/statistics/natlpatterns/) (4) using visualization, presenting the data in new and useful ways, i.e., can the data be linked to show cross-agency funding by discipline or scientific area, e.g. by nanotechnology, as well as who is funding research? Can the data be linked to publications to show impact and networks?

- Importance to sponsor. This project will allow the NCSES sponsor to learn about the feasibility of accessing and analyzing non-survey data about public R&D.

- Importance to SDAD. This project contributes to the SDAD-NCSES portfolio of projects to measure science and engineering concepts using non-traditional data, (i.e., non-survey).

- Prior work. We will review existing NCSES data collected about public R&D expenditures (https://www.nsf.gov/statistics/natlpatterns/)

- Student involvement. Students will 1) discuss the ethical implication of the research starting with a review of the NCSES project IRB protocol, project goals, and other relevant materials; 2) use Data Science Framework to  discover learn about public R&D expenditure data; (3) scrape or download data from federal websites; (4) explore data for consistency, etc. (5) compare to existing public R&D data,(6) document results on SDAD wiki; 7) review and summarize ethical insights and conclusions. See attached timeline for complete set of activities.

- Request for students. The project requests 1 graduate students and 2 undergraduate students. Ideal students are skilled R users with experience webscraping and summarizing data for use in analysis.

Expectations.

The project will deliver 1) documentation about public R&D expenditures across federal agencies using a common template; 2) data acquisition; 2) Sage brief for online publication (  https://www.methodspace.com/, https://www.socialsciencespace.com/, orhttps://psmag.com/ ) 3) DSPG symposium poster and presentation.

NSF National Center for Science and Engineering Statistics (NCSES): Measuring the Public Funding of R&D Projects – a pilot study

|  |  |  | DSPG 2019 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 |
| PHASE |  | TASKS | 5/28 - 5/31 | 6/3 - 6/7 | 6/10- 6/14 | 6/17 - 6/21 | 6/24 - 6/28 | 7/1 - 7/5 | 7/8 - 7/12 | 7/15 - 7/19 | 7/22 - 7/26 | 7/29 - 8/2 | 8/5 - 8/9 |
| Training | Ethics | Complete IRB, RCR, and COI trainings. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete/review ARI project ethics checklist. |  |  |  |  |  |  |  |  |  |  |  |
|  | Skills | Complete tidyverse and data wrangling courses, as needed. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete other DSPG courses, as needed. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete git courses, as needed. |  |  |  |  |  |  |  |  |  |  |  |
|  | Workflow | Review documentation standards. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Review collaboration tools – SDAD wiki. |  |  |  |  |  |  |  |  |  |  |  |
| Data | Discovery | Review NCSES R&D documentation, https://www.nsf.gov/statistics/natlpatterns/ |  |  |  |  |  |  |  |  |  |  |  |
|  | Inventory | Create questions & template to access |  |  |  |  |  |  |  |  |  |  |  |
|  | Screen | Create detailed questions to delve more deeply into data |  |  |  |  |  |  |  |  |  |  |  |
|  | Document | Describe data sources at each federal science agency; assess feasibility of acquiring data and prioritize order of access |  |  |  |  |  |  |  |  |  |  |  |
|  | Acquire | For selected agencies, download or scrape data |  |  |  |  |  |  |  |  |  |  |  |
| Literature | Read | Read selected literature on uses of public R&D data (e.g. AAAS, NAS reports, NSF website). |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Integrate literature review into Sage briefs (draft). |  |  |  |  |  |  |  |  |  |  |  |
| Use Cases | Profile | Select and profile relevant variables for comparisons and analysis |  |  |  |  |  |  |  |  |  |  |  |
|  | Clean | Clean variables as needed for research. |  |  |  |  |  |  |  |  |  |  |  |
|  | Integrate | Prepare data for analysis. |  |  |  |  |  |  |  |  |  |  |  |
|  | Explore | Visualize and analyze data |  |  |  |  |  |  |  |  |  |  |  |
| Analysis |  | Prepare summary of findings |  |  |  |  |  |  |  |  |  |  |  |
| Communication | Stakeholder | Meet with stakeholder. |  |  |  |  |  |  |  |  |  |  |  |
|  | Poster | Complete symposium poster(s). |  |  |  |  |  |  |  |  |  |  |  |
|  | Brief | Draft and prepare publication-ready Sage brief(s). |  |  |  |  |  |  |  |  |  |  |  |