Charter for the Internal NCSES Working Group on

Measuring the Skilled Technical Workforce

Draft – March 6, 2019

Objective

The National Academies,,, the National Science Board, and recently proposed legislation have mentioned the need for and potential usefulness of data on the skilled technical workers – defined as individuals in occupations that require a high level of knowledge in a technical domain but do not require a bachelor’s degree for entry. Unfortunately, as noted in the National Academies of Sciences, Engineering, and Medicine 2017 report, Building America’s Skilled Technical Workforce, a lack of information about skilled technical workers makes it difficult for policy makers, employers, and workers to address issues in the skilled technical workforce development policies, processes, and programs. Simply put, policy makers and labor market participants need better data and more useful data tools with which to analyze labor market dynamics.

As a unit within the National Science Foundation (NSF), the National Center for Science and Engineering Statistics contributes to NSF’s mission to create a STEM-capable U.S. workforce, and has developed a broad understanding of the policy issues that concern skilled technical workers. Thus, NCSES is in a unique position to champion a coordinated effort among federal statistical agencies to address the lack of information on the skilled technical workforce.

This charter establishes an internal NCSES working group with the goal of developing an action plan to guide NCSES efforts to measure and understand the skilled technical workforce.

Background

The pervasiveness of science and technology in the economy has changed the nature of work for individuals at all education levels, including those without a 4-year degree. There are over 16 million skilled technical jobs for workers with an associate degree, or similar qualification rather than a bachelor’s degree. The individuals who use science, technology, engineering, and math (STEM) knowledge and skills in their jobs but who do not have a 4-year degree make up the skilled technical workforce (STW).

Skilled technical workers are important to U.S. economic competitiveness. Businesses cite the availability of highly skilled workers as critical to their ability to compete globally, yet regularly express difficulty in finding workers to fill these jobs. The STW also plays an important role in advancing our national security. Industries that are critical to our national security and defense—including aerospace, advanced manufacturing, information technology, healthcare, and cybersecurity—rely on access to these workers. The STW is also important to scientific progress. Industry representatives estimate that they need between 7–20 skilled technicians for every scientist or engineer with an advanced degree.

There are several ways that individuals gain these skills, including military training, apprenticeships, associate degrees, and certificate programs. Given the flexibility, accessibility, and relative affordability of the programs they offer, community and technical colleges serve as a key entry point into the STW for students from all backgrounds. They provide these students with linkages to local industry, but also empower them to pursue further education and follow multiple pathways into STEM careers.

Working group activities

To meet its goal of developing an action plan to guide NCSES efforts to measure and understand the STW, the working group will pursue a multidimensional initiative that includes the following activities:

- STW working definition determination – Identification of a STW working definition for both policy discussion and quality measurement

- Stakeholder outreach and needs determination – Development of a communication plan and outreach document that provides NCSES management, partners, and stakeholders with an overview of the milestones, timing, and progress for the working group; Formation of workshops, technical review panels, and other outreach efforts to understand stakeholders’ STW information needs and explore methods for developing STW measures

- Survey data analysis – Evaluation of employee and employer data from federal surveys as potential sources for STW estimates

- Administrative data analysis – Evaluation of employee and employer administrative data as potential sources for STW estimates6

- Survey development – Evaluation of sampling frame options, determination and testing of survey content, and development of a sample design approach and data collection methodology for a nationally representative training, education, and workforce survey to measure the STW

- Project management – In addition to the development of the activity-specific deliverables described below, a mid-term progress report and a regularly updated outreach document are also planned to provide insight on the status of the working group

Working group organization and membership

Given the activities noted above, the working group should have representation from the Human Resources Statistics program (HRS), Science and Engineering Indicators program (SEI), and the Statistics and Methods Program (SMP). A working group kickoff meeting will initiate discussions on a detailed work plan and assignments/projects. The deliverables and tentative timing section of this charter will serve as a starting point for these discussions. The kickoff meeting would be followed by biweekly meetings (on an as needed basis) supplemented with internal exchanges.

Activities will conclude by March 2020, though the working group terms may be extended depending on progress on remaining activities or new NCSES-wide needs. The membership of the working group is as follows:

| Title | Participant | Role |
| --- | --- | --- |
| Champion | Emilda Rivers | Serve as an advocate for the working group’s efforts |
| Chair | John Finamore | Provide oversight to the direction and activities of the working group |
| Member | HRS STW Project Officer (To be determined) | Provide project management oversight to the specific activities conducted by this working group including the stakeholder outreach and needs determination, analysis of data sources, and survey development |
| Member | Flora Lan (HRS) | Provide contractual oversight to task order contacts to supplement the working group’s efforts |
| Member | HRS representative (To be determined) | Provide project management oversight of the UVA-SDAL efforts to measure non-traditional STEM pathways |
| Member | Karen Hamrick (HRS) | Provide analytical subject matter support related to the HRS program’s efforts to measure the STW |
| Member | Amy Burke (SEI) | Provide analytical subject matter support related to the SEI program’s efforts to measure the STW |
| Member | John Trapani (SEI) | Provide analytical subject matter support related to the SEI program’s efforts to measure the STW |
| Member | Jen Beck (SMP) | Provide survey methodological support |
| Member | Matt Williams (SMP) | Provide mathematical statistical support |
| Member | Ashley Begley (SRI) | Meeting minute taker and caretaker of the outreach document |

Partners

For this working group, we define partners as individuals, agencies, or organizations that are conducting work to inform STW policy discussions and decisions. Given the essential role of skilled technical workers in our economy, security, and science, multiple agencies and organizations have begun efforts to measure the STW. In response to the content, statistical, analytical, and project management complexities of the broad effort to understand the STW, the efforts of this working group will seek partnerships with other agencies and organizations. The working group chair will coordinate with the partners through working group members serving as partner liaisons.

| Partner | Activity to inform STW policy discussion | NCSES liaison |
| --- | --- | --- |
| National Center for Education Statistics (NCES) | Conducted the 2016 Adult Training and Education Survey (ATES); Assist in the development of a nationally representative training, education, and workforce survey | John Finamore |
| Census Bureau (Associate Directorate for Demographic Programs) | Assist in the development of a sample design approach and data collection methodology for a nationally representative training, education, and workforce survey to measure the STW | HRS STW Project Officer |
| Census Bureau (Center for Administrative Records Research and Application) | Conduct research using administrative data to examine the STW | HRS STW Project Officer |
| University of Virginia - Social and Decision Analytics Division | Conduct collaborative research with NCSES using administrative data to examine non-traditional STEM pathways | HRS Representative |
| Department of Labor | Disseminate various online data tools to better understand education and occupation credentials (e.g., CareerOneStop) | John Finamore |
| Bureau of Labor Statistics (BLS) | Manage O*Net, the Current Population Study, and other data products that provide an increased understanding of the STW | John Finamore and Emilda Rivers |
| National Science Board (NSB) | Established the Task Force on the Skilled Technical Workforce | Amy Burke |
| NSF Directorate for Education and Human Resources (EHR) | Initiated the advanced technological education (ATE) program to support the education of science and engineering technicians | Josh Trapani |
| American Institutes for Research | Subcontractor to NCES in the conducting of the 2016 ATES; Assist in the development of a nationally representative training, education, and workforce survey | John Finamore |
| SRI International | Subcontractor to NCSES for STW research | Flora Lan |

Stakeholders

For this working group, we define stakeholders as individuals, agencies, or organizations that are seeking information about the STW for use in decisions and policy discussions. The working group chair will coordinate with the stakeholders through working group members serving as stakeholder liaisons.

| Stakeholder | Information needs | NCSES liaison |
| --- | --- | --- |
| Policymakers | To be determined (TBD) | TBD |
| Employers | TBD | TBD |
| Skilled technical workers | TBD | TBD |
| Researchers | TBD | TBD |
| Professional associations | TBD | TBD |
| The general public | TBD | TBD |

Deliverables

The working group will submit deliverables for each of the activities described in this charter. The NCSES leadership team is the intended audience for all working group deliverables. The table below describes the aforementioned activities, the corresponding deliverables, and the proposed working group point of contact for each deliverable.

| Activity |  | Deliverable | Point of Contact |
| --- | --- | --- | --- |
| Number | Description |  |  |
| 1 | STW working definition determination | Memorandum documenting the STW working definition and the justification for the definition | Ashley Begley |
| 2 | Stakeholder outreach and needs determination | Memorandum documenting the communication and outreach strategy, including a template for a monthly outreach document that provides an overview of the milestones, timing, and progress for the working group | Ashley Begley |
|  |  | Formation of two workshops/technical review panels (TRP) | HRS STW Project Officer |
|  |  | Summary notes document from each workshop/TRP | Ashley Begley and Karen Hamrick |
|  |  | Memorandum identifying specific STW information needs based on workshop/TRP discussions | Josh Trapani and Amy Burke |
| 3 | Survey data analysis | Memorandum documenting the results of an evaluation of employee and employer data from federal surveys as potential sources for STW estimates. The memorandum should include recommendations for NCSES based on the evaluation results. | John Finamore and Karen Hamrick |
| 4 | Administrative data analysis | Memorandum documenting the results of an evaluation of employee and employer administrative data as potential sources for STW estimates. The memorandum should include recommendations for NCSES based on the evaluation results. | HRS Representative |
| 5 | Survey development | Memorandum documenting the results of an evaluation of sampling frame options for a national survey. The memorandum should include recommendations for NCSES based on the evaluation results. | Matt Williams |
|  |  | Memorandum documenting the results of an evaluation to determine and test survey content for a national survey. The memorandum should include recommendations for NCSES based on the evaluation results and should include a section summarizing why we need each content item (modeled after the “Why We Ask” document for the American Community Survey). | Amy Burke and Jen Beck |
|  |  | Memorandum documenting the results of an evaluation to develop a sample design approach and data collection methodology for a national survey. The memorandum should include recommendations for NCSES based on the evaluation result (e.g., proposed survey design and operations plan) | HRS STW Project Officer, Matt Williams, and Jen Beck |
| 6 | Project management | Outreach document that provides an overview of the milestones, timing, and progress for the working group (updated monthly) | HRS STW Project Officer |
|  |  | Mid-term progress report | HRS STW Project Officer |
|  |  | Memorandum issued at the conclusion of the working group’s effort that provides an action plan with specific tasks to guide NCSES efforts to measure and understand the skilled technical workforce | John Finamore |

Tentative Timing

- March 2019: Approval of charter, formal establishment of working group, and kickoff meeting

- April 2019: Development of draft concept approval outlines for each deliverable (as appropriate) and establishment of a schedule for working group deliverables

- May 2019: Delivery of a communication plan memorandum and outreach document template (deliverable under activity #2)

- September 2019: Mid-term progress report

- March 2020: Delivery of the final deliverable and working group closeout

Completed tasks

- STW working definition

- Implemented the Rothwell (2015) STW definition methodology using updated OES and ACS data

- Documented the Rothwell (2015) STW definition methodology implementation

- Stakeholder outreach and needs determination

- Discussed information needs with NCES, NSF, Census Bureau, and the National Science Board Task Force on the Skilled Technical Workforce

- Survey data analysis

- Derived and evaluated STW estimates using 2016 Adult Training and Education Survey data

- Derived and evaluated STW estimates using 2016 Current Population Survey data

- Derived and evaluated STW estimates using 2016 American Community Survey data

- Evaluated the Job Openings and Labor Turnover Survey data

- Administrative data analysis

- Evaluated Burning Glass Technology job postings and resume data

- Evaluated administrative data sources from the Virginia Department of Education (VDOE) and the State Council of Higher Education in Virginia (SCHEV)

- Evaluated Virginia Tech’s Open Data Open Jobs administrative data

- Evaluated University of Chicago’s Data at Work administrative data

- Survey development

- Determined sample size needs under a two-stage sample design using an address-based sampling frame

- Determined sample size needs under a two-phase sample design using the American Community Survey as the sampling frame

- Conducted cognitive testing for variations of questions included in the 2016 Adult Training and Education Survey to address STW information needs

- Developed a web instrument specification for a nationally representative training, education, and workforce survey

- Developed a paper and pencil instrument specification for a nationally representative training, education, and workforce survey

- Developed a proposed data collection methodology and contact strategy for a nationally representative training, education, and workforce survey

- Proposed methodological research experiments involving contact strategies and incentive usage for a nationally representative training, education, and workforce survey

National Research Council, Committee on National Statistics. (1989).  Surveying the Nation’s Scientists and Engineers:  A Data System for the 1990s. Washington: National Academy Press.

National Research Council. (2008). Using the American Community Survey for the National Science Foundation’s Science and Engineering Workforce Statistics Programs. Washington, DC: The National Academies Press.

National Academies of Sciences, Engineering, and Medicine. (2017). Building America’s Skilled Technical Workforce. Washington, DC: The National Academies Press.

National Science Board (2017). Task Force on the Skilled Technical Workforce. National Science Foundation. Available: https://www.nsf.gov/nsb/committees/stwcmte.jsp [December 13, 2018].

Committee on Science, Space, and Technology (2018). H.R. 5509, The Innovations in Mentoring, Training, and Apprenticeships Act April 13, 2018. Available: https://science.house.gov/legislation/bills/hr-innovations-mentoring-training-and-apprenticeships-act. [December 13, 2018].

The examination will consider the availability, coverage, reliability, granularity, and sustainability of estimates.

The working group’s survey development effort will follow the guidance provided in the Office of Management and Budget’s memoranda on Guidance on Agency Survey and Statistical Information Collection (2006) and Standards and Guidelines for Statistical Surveys (2006) and NCSES’s Supplemental Guidelines for New Survey or Major Revisions of Existing Surveys (2008).

The partnerships and stakeholders will likely evolve as the work of the working group progresses. To ensure NCSES management obtain an understanding of the broad effort to measure the STW, the list of partners and stakeholders will be updated on a regular basis in the working group’s outreach document.