Solder Characteristics that Contribute to Unit Performance: A Qualitative Analysis

Sponsor: The Army Research Institute for the Behavioral and Social Sciences (ARI)

Project goal: Engage in qualitative research work to inform and contextualize quantitative modeling.

- Primary research question: What are the characteristics of individual Soldiers that contribute to unit performance?

- Additional topics of interest/Secondary research questions:

  - What are possible indicators or measures we could use to assess contextual, counterproductive, and adaptive performance?

  - Are the same or different characteristics highlighted as important across Army documents and the academic literature?

  - What is the role of team composition (versus individual characteristics)?

  - How are these characteristics connected to soft skills/skill articulation?

  - What behavioral indicators are associated with the characteristics and do comparable indicators exist in our Army data?

Legend:

- Interns

- SDAD

Legend:

- Interns

- SDAD

Major project tasks and outputs/deliverables:

- Review previous ARI-related work

  - Our Performance Framework

  - Previous qualitative analysis and corpus of Army documents

  - Statistical modeling and Army data we’re using

- Other Army background

- Training and prep work

  - Training on Dedoose software – Christine Slaughter from library

  - Develop a Document Analysis Record

    - Read selected documents

    - Populate additional columns

    - Identify additional sources of documents

  - Use Document Record identified documents appropriate for research questions

    - Refine research questions

  - Access documents

    - Do any documents need to be analyzed over time?

  - Iterative with stakeholder to assess if documents are appropriate

  - Upload and organize documents in Dedoose

  - Document appropriate metadata (document types/definitions, years)

- OUTPUT: Conduct a Document Review

- Explore content

  - Thematic analysis

    - Hybrid inductive/deductive approach to review documents for themes

    - A-priori codes established based on a review of the literature, quantitative modeling, and stakeholder input

    - Emergent codes

  - Small team coding with reliability checks

  - Dedoose Testing Center

  - Assign primary coders to documents/who will take the tests

  - Set up the tests

  - Run meetings to reconcile codes

  - Reconcile codes

  - Reviewer notes

  - Aiming for good agreement or better

    - e.g., Pooled Cohen’s Kappa of 0.61 or greater

    - Research this, other metrics of agreement

- Triangulation

  - We can provide some ideas, but the point is to let the analysis “unfold” in the direction the team thinks is most appropriate

  - What additional data could add robustness to this analysis? / Confirm/deny/contextualize themes

    - Discovery of more documents to address a secondary research question?

      - e.g., diving deeper into team composition

      - From a talent management perspective, we have read about the importance of balance in the composition of the Army (commission source, women in high ranks etc.)

      - How does this translate to team composition? How might we model “balance” in the Army? What kinds of variables contribute to this?

    - Conversations with Army officials/Soldiers? Who? What would we ask? (Not realistic but knowing who we would want to talk to and what we would ask might be interesting)

    - Additional scholarly literature, conversations with scholars

    - Additional Army documents/recruiting materials/videos/images etc.

    - Other types of analysis, NLP, networks

- Write-up of results

  - OUTPUT: Poster

    - Pulling out examples

    - Reconciling reviewer notes

    - Elimination of irrelevant a-priori codes

  - OUTPUT: Wish list of variables + composites (Where are the gaps?)

  - OUTPUT: Thematic map

Legend:

- Must do-s

- Nice to have

Legend:

- Must do-s

- Nice to have

| Week | Major activities | Goal Outputs |
| --- | --- | --- |
| Week 1: 5/30-6/3 6/3: Joel out | Day off – Memorial Day 1-2 days Review of ARI Work Review of Qualitative work Other Army Background |  |
| Week 2: 6/6-6/10 6/10: Joel out | 6/6 Dedoose training 2pm 4-5 days Improve document analysis record Work on document review 1 day Document analysis research plan | Document Analysis Record Document Review |
| Week 3: 6/13-6/17 6/13-6/16: Joel and Joanna at MORS 6/17: Joel out | MORS 1 day Document analysis research plan 4-5 days Document analysis / How’s it going? Army vs academic literature, go out and search for new things Thinking about triangulation | Document Analysis Research Plan, i.e., Which Documents, Who is reviewing what on what days, etc. |
| Week 4: 6/20-6/24 6/20-6/24: Joel at training event | Day off – Juneteenth 4 days Document analysis Writing up results Thinking about triangulation |  |
| Week 5: 6/27-7/1 | Mid-term 2-3 days Finish up analysis Write-up results Create presentation 2-3 days Decide on triangulation, begin planning | Finish Document Analysis Midterm presentation Write-up of results (ongoing) |
| Week 6: 7/4-7/8 | Day off – Independence Day 1-2 days Planning/preparing for triangulation 1-2 days Triangulation | Review write-up of first part results on 7/8 Start on final write-up on 7/8 |
| Week 7: 7/11-7/15 | 1-2 days Finish recoding on Dedoose 3 days Upload 9 coded docs and cleaning Triangulation | Write-up of results (ongoing) |
| Week 8: 7/18-7/22 | 5 days Triangulation Compare qual codes against EDA Individual analysis of 9 docs Compare 9 docs against ‘green’ docs Finish triangulation | Write-up of results (ongoing) |
| Week 9: 7/25-7/29 7/25-7/29: Joanna out | 1 day Finish triangulation 4 days Prepare final materials | Draft PowerPoint -based off of write-up Wish list of variables + composites Thematic map |
| Week 10: 8/1-8/5 | 5 days Finish preparing final materials | Final PowerPoint |