DSPG Summer Project – Impact of Broadband Programs

Project Sponsor

- John Pender, USDA Economic Research Service

SDAD team

- Aritra Halder

- Josh Goldstein

- Hanna Charankevich

Project Goal

USDA would like to know whether broadband development has an effect on broadband adoption and rural prosperity, as measured by changes in property values and quality of life indicators in rural communities. We will examine the impact of programs that develop broadband infrastructure, with a focus on grants and loans from the USDA Rural Utility Service (RUS). The first part of the project will examine RUS program effects on rates of broadband adoption, measured using Ookla speedtest data. The second piece will use housing and tax assessment data provided by CoreLogic, along with sociodemographic data from the American Community Survey (ACS) to look at program impacts on property values.

Student Involvement

- Clean CoreLogic housing and tax assessment data.

- Link housing data to RUS broadband programs.

- Link Ookla speedtest data to RUS broadband programs.

- Implement spatial statistical methods to assess broadband program impacts, including regression discontinuity and spatial gradient assessment.

The team will require 2 students -- experience with R is helpful. Students will learn methods for spatial statistical modeling.

Expectations / Deliverables

- Data products:

  - Ookla data linked to RUS programs

  - Cleaned CoreLogic assessment data linked to RUS programs

- EDA + Midterm presentation

- Final poster and presentation

- Project documentation

TIMELINE

Week 1: 5/31-6/3

- Introductions and project teams

- Project background review

- Literature review: Broadband programs

Week 2: 6/6-6/10

- Meeting with USDA ERS sponsor John Pender

- Literature review: Broadband programs

- Ingesting CoreLogic data

- Linking Ookla data

Week 3: 6/13-6/17 (Josh at MORS conference) (Aritra at NSF Workshop 6/13 – 6/14)

- Literature review: Spatial methods

- Cleaning/linking CoreLogic data

- Linking Ookla data

- Exploratory Data analysis

Week 4: 6/20-6/24 (Monday: UVA Holiday – Juneteenth)

- Literature review: Spatial methods

- Cleaning/linking CoreLogic data

- Analysis of Ookla data

- Exploratory Data analysis

Week 5: 6/27-7/1 (Aritra at ISBA from 6/26 – 7/1)

- Cleaning/linking CoreLogic data

- Analysis of Ookla data

- Exploratory Data analysis

- Midterm presentation

Week 6, 7, 8: 7/4-7/22

- Implementing statistical models to measure impact of RUS programs:

  - Broadband adoption using Ookla

  - Property values using CoreLogic

Week 9: 7/25-7/29

- Continue statistical analysis

- Draft of final presentation

Week 10: 8/1-8/5

- Documentation

- Final presentation