DSPG Summer Project – Coastal Futures: Building Capacity for Data-driven

Adaptation in Rural Coastal Communities

SDAD Team: Josh Goldstein

Project Description:

Rural coastal communities face difficult challenges responding to climate risks, particularly by saltwater intrustion frorm accelerated sea level rise and storm flooding. This work is part of a collaboration with UVA’s Environmental Resilience Institute. This project is part of a collaboration with UVA’s Environmental Resilience Institute to study climate impacts on the rural Eastern Shore of Virginia (ESVA), with the goal of developing tools and building the capacity for communities to deal with these impacts. We will develpop a synthetic population that represents these communities by combining information across multiple sources of data, administrative and survey data, to get a representation of these rural communities down to the level of individual households and farms. This will be used as an input into agent based models for stakeholder decisions, and hydrological models to measure flood hazard, water supply, and groundwater salinization.

Student Involvement

- Project background and literature review on climate risks

- Data discovery and inventory to characterize households and farms in ESVA

  - Data acquisition, cleaning, linking

- Help to construct a synthetic population for Accomack and Northampton counties using Iterative Proportional Fitting

- Apply demographic projections to predict how these populations will change over the next several decades

The team will require 2 students.

Expectations / Deliverables

- Literature review

- Documented data discovery

- Realizations of synthetic households and farms

- County-level demographic

- Final poster and presentation

- Project documentation

TIMELINE

Week 1: 5/31-6/3

- Introductions and project teams

- Project background review

- Literature review: Climate risks and synthetic methods

Week 2: 6/6-6/10

- Data discovery

- Literature review: Climate risks and synthetic methods

- Meet with Sarah Nusser: data sources

Week 3: 6/13-6/17 (Josh at MORS conference)

- Data discovery

- Literature review: Climate risks and synthetic methods

- Exploratory data analysis

Week 4: 6/20-6/24 (Monday: UVA Holiday – Juneteenth)

- Data discovery

- Exploratory data analysis

- Meeting with Joe Salvo: Census methods for demographic projection

- Meet with Henning Mortveit: data sources used by NSSAC

Week 5: 6/27-7/1

- Data discovery

- Exploratory data analysis

- Creating synthetic populations with IPF

- Midterm presentation

Week 6-8: 7/4-7/22

- Creating synthetic populations with IPF

- Applying methods for demographic projection

Week 9: 7/25-7/29

- Creating synthetic populations with IPF

- Applying methods for demographic projection

- Draft of final presentation

Week 10: 8/1-8/5

- Documentation

- Final presentation