Two 50% time students

Must do-s

Nice to have

| Week | Major activities | Goal Outputs |
| --- | --- | --- |
| Week 1: 5/30-6/3 5/30-6/3: Kathryn out | Day off – Memorial Day - days -Review of R&D past and current work -Read R&D Tech Report and Paper -Background on NLP, topic modeling, information retrieval | Leonel to meet with students to provide and give high level overview of the R&D Tech paper and Journal Paper and answer questions. Discuss and answer questions on Friday/Monday. |
| Week 2: 6/6-6/10 6/10: Joel out | 4-5 days -Continue learning background information from last week -Explore Federal RePORTER dataset and complete basic EDA -Review/explore current project code |  |
| Week 3: 6/13-6/17 6/14, 6/16, 6/17: Joel out | 6/15: Meeting with NCSES sponsor 4-5 days - Research digitalization theme (literature search) - NASEM, OECD, Journal Literature, etc. | Slide deck for weekly meeting: what is Digitalization? |
| Week 4: 6/20-6/24 6/20-6/24: Joel at training event | Day off – Juneteenth 4 days -literature search and brainstorm on information retrieval (how to identify abstracts about digitalization) |  |
| Week 5: 6/27-7/1 Stephanie is out this week. | Mid-term 2-3 days -Finish up information retrieval brainstorm 2-3 days -Test information retrieval methods | Midterm presentation? Slide deck for weekly meeting: information retrieval methods to identify digitalization abstracts |
| Week 6: 7/4-7/8 Stephanie is out this week. | Day off – Independence Day 4 days -continue testing of information retrieval methods |  |
| Week 7: 7/11-7/15 | 5 days -finish testing information retrieval methods and decide on final strategy If time -Data discovery for federal grant data, agency TBD | Slide deck for weekly meeting: information retrieval testing |
| Week 8: 7/18-7/22 | 7/20: meeting with NCSES sponsor 5 days -Complete topic trend results If time -continued data discovery -fitness-for-use testing of grant data -wrangling of grant data |  |
| Week 9: 7/25-7/29 | 5 days -Prepare final materials If time -complete fitness-for-use testing and wrangling | Draft poster Wrangled [agency TBD] dataset |
| Week 10: 8/1-8/5 | 5 days -Finish preparing final materials -Present to NCSES Sponsor 8/4 or 8/5 | Final Poster |