DSPG 2017 Debrief and potential plans for 2018 to be discussed with SDAL:

- Scheduling

DSPG 2018

| Week | DSPG dates | VT Calendar |
| --- | --- | --- |
| Wk 1 - May 21-25 | DSPG Fellows start | VT Summer I Classes start on May 21 |
| Wk 2 - May 29-Jun 1 | DSPG Students start |  |
| Wk 3 - Jun 4-8 |  |  |
| Wk 4 - Jun 11-15 |  |  |
| Wk 5 - Jun 18-22 |  | VT Summer I Exams begin on June 29 |
| Wk 6 - Jun 25-29 | DSPG midterm presentations | VT Summer I Classed End on June 28 VT Summer I Exams end on June 30 |
| Break - Jul 2-6 |  | VT Summer II classes start on Jul 2 |
| Wk 7 - Jul 9-13 |  |  |
| Wk 8 - Jul 16-20 |  |  |
| Wk 9 - Jul 23-27 |  |  |
| Wk 10 - Jul 30-Aug 3 | JSM attendance |  |
| Wk 11 - Aug 6-10 | DSPG Student Final Week August 9th DSPG Symposium | VT Summer II Classed End on Aug 9 VT Summer II Exams end on Aug 11 |
| Wk 12 - Aug 13-17 | DSPG Fellows wrap-up |  |

- Staffing

- ~15 undergraduate students

- 5 fellows

- DSPG Alumni: Maddie, Eirik, etc.

- Design: SDAL will be asked individually regarding topics such as:

  - Project allocation to faculty and students (project per student/faculty)

  - Weekly kick-off and wrap-up meetings

  - Survey results from last summer

- SDAL faculty responsibilities

- Project proposals, and selection with Sallie

- Participation in fellow/student screening, and interviews

- Arrange interaction with project sponsors

- Faculty presence & attendance to project meetings

- Student performance monitoring and early action

- Mentorship

- Trainings/Brownbags

- Symposium

- Save the date: August 9th

- Attendance important

- Outreach

- Keynote speakers?