## Sheet1
| hours |  | Poster Session | honors
Start planning (Gizem and Aaron) |  | 2017-12-15 | Dates | Shernita
weekly meetings with Sallie and Kim |  | 2017-12-15 | Reserve Room | Meet Pauls
Application survey finalize
Survey live |  | December?
SDAL Website finalize |  |  | Keynote speakers | Promo docs | 2017-12-05
Announcements |  |  | Support application | Course document
Inform HR |  |  |  | HR documents
applications due |  | 2017-02-01 |  | Announce program
Interviewee selection |  | 2017-02-16 |  | Reach out
Email selected students |  | 2017-02-17
Interviews | 13*0.5 | Feb 21 - Feb 28 |  | Info emails
Regrets to non-interviewees |  | March 1st
Ranking and finalize with Sallie |  | March 1st |  | Deadline
HR Contact Erin Cassidy |  | March 1st |  | Receive applications
Rejection emails to interviewed |  | 2017-03-03
Acceptance Letter sent out |  | 2017-03-03 |  | Send acceptance letters
Deadline to accept |  | 2017-03-10
Offers sent out |  |  |  | Surveys
Final emails to students |  | 2017-03-17 |  | IT stuff
IRB training