Draft May 20, 2017 – DSPG project

Identifying and Predicting Effects of Trends on Youth Population in Fairfax County

Project Sponsor/Collaborator

Fairfax County Division for Countywide Service Integration and Planning Management (CSPIM), Neighborhood and Community Services (NCS), within Health and Human Services (HHS)

Proposed Team

SDAL – Stephanie Shipp, Vicki Lancaster, Aaron Schroeder

Fairfax - Sophia Dutton Sophia.Dutton@fairfaxcounty.gov

Hoffman, Linda Linda.Hoffman@fairfaxcounty.gov

DSPG students: 2 graduate students with at least one in statistics and 2 undergraduates

Research Questions

- Which HHS programs and services may be affected by changes in population size, behaviors, and demographic makeup?

- What current and future trends in demographics, housing, and other factors would inform the models to predict changes in their programs?

- What are trends in the data that warrant more investigation? e.g., Why are kids engaging in less and less physical activity?

Project Description.

Fairfax HHS is interested in developing long-term population and economic forecasting capabilities to complement their short-term planning activities. The goal is to determine which HHS programs and services may be affected by changes in population size, behaviors, and demographic makeup. NCS is interested in understanding the range of data sources, e.g., local, state, and federal, that can be used to develop meaningful forecasts.

This project will focus on developing an initial set of forecasts associated with youth behaviors (e.g., physical activity, suicide ideation, e-cigarettes), in Fairfax County. The specific behaviors will be informed by the Fairfax County Youth Services surveys, combined with other data sources, e.g. demographics, housing, parks and recreation, and other data.

This project will use a combination of Fairfax County Youth Survey Data (from 2010 onward), along with other data sources (e.g., local and state administrative data, designed state and federal data collections with local aggregates, and local social media).

What are students expected to do in steps

Weeks 1-2

  - Read materials on the Fairfax Human Services website:

- The survey instruments can be found online here -http://www.fairfaxcounty.gov/demogrph/youth_survey_administration.htm

- The reports for the Youth Survey, highlights video, fact sheets, etc. can be found at www.fairfaxcounty.gov/youthsurvey.

  - Meet with Fairfax sponsors to identify issues and potential research questions.

  - Develop and refine research questions will involve reviewing the topics on the Fairfax County Youth Survey and meeting with the Neighborhood and Community Services (NCS) to determine which topics would be most appropriate for developing a first set of forecasts, (e.g., physical activity, suicide ideation, e-cigarettes, etc.).

Weeks 3-5

  - The literature review will review what similar studies and youth surveys have been done nationally as well as reports and documents directly associated with Fairfax County youth.

  - The data discovery will review data sources already identified by NCS through their Results Areas “determinants” activities. Additionally, the data discovery will be guided by the literature review and research question formulation to identify other data sources, including administrative data and social media, from local, state, and federal activities.

Weeks 6-8

  - The data fitness assessment will evaluate available data sources for issues of completeness, value validity, consistency, uniqueness, duplication, as well as issues of data structure. The results of these analyses will help determine what necessary transformations/cleaning might be needed as well as the fitness of the data for use in further analysis.

  - The data integration and statistical analysis will produce longitudinal profiles of the county by relevant geographic areas (e.g., high-school boundaries, supervisor areas) and relevant to the research questions. These findings will inform the construction of forecast models.

Week 9-10

Prepare report and poster documenting above steps and presenting literature review, data discovery, data fitness assessment, and data integration and statistical analysis.

Expected outputs

- Document work on wiki and in short 2-3 page write-ups summarizing results.

  - Literature review on youth behaviors under consideration.

  - Execution of the SDAL data framework to discover, profile, clean, and transform data sets in preparation for data analysis.

  - Catalog of available data sources that include: source of the data, a list of variables, observational unit(s), geographic area covered, how often the data are updated, etc.

  - Project findings and the analyses to support the findings.

  - Outline of future steps to strengthen insights and capabilities for a broader set of population and economic forecasts for Fairfax County HHS programs and activities.

  - Poster and presentation summarizing the above outputs