VT DSPG 2017 –discussed with SDAL-

This year DSPG Program will have around 10 VT Honors and Honors eligible students as undergraduate students (to be finalized in May – see current list attached); and 5 graduate students across the country (information attached). We will also have ex-DSPG students Madison and Adrienne; and Daniel to help with the execution of the program.

Teams of three or four students and proposer (lead) will spend the summer tackling SDAL projects (~10-12 projects). Project teams will be horizontally and vertically integrated: each project team will have undergraduate students with different backgrounds/skill levels, a graduate student, and a postdoc/faculty from SDAL depending on the scope of the project. Students will work on 2-3 projects (one major and minor projects), so that they benefit from seeing the particular challenges that arise in a variety of projects and with variety of data sources.

During the first day of program, the information you provide will be used to present the projects to the students, and the students will request projects, and team assignments will be finalized.

RESPONSIBILITIES

SDAL Staff:

• Mentorship of students

• As project lead, s/he should provide the team with background knowledge about the problem, and s/he is responsible for access to lightfoot folders/wiki/representative data if it applies.

• Project meetings. The project lead should be available to meet with the team at least once every two weeks.

Graduate Student:

• Responsible for production of timely deliverables according to the project timeline, notifying any problems to the project lead and DSPG leads.

• The graduate student will meet with the team frequently, to provide technical insight to support the solution strategy and to point the team toward techniques, algorithms, or software.

Undergraduate Students:

• Weekly updates. Teams will give weekly informal presentations (every Friday).

• Final presentation. At the end of the semester, each team will summarize their findings in a poster session. Sponsors/collaborators and SDAL friends are invited to attend these presentations.

• Reports. Each team will also develop a mid-term and a final report that summarizes background, limits of current practice, their problem-solving process, novelty of the approach, and that presents the final results.

TRAININGS

Organizers: Aaron (and Daniel)

Syllabus at https://github.com/bi-sdal/workshop

* Intro to Data Science

* Intro to Bash

* Intro to SDAL Servers

* Intro to R

* Intro to Git

* R-GIS

* Getting and Fixing Data with R

* Databases (PostgreSQL)

* Analyzing Data with R

* Exploratory Analysis

* Reporting Data with R

* Webscraping

BROWNBAGS / SEMINARS

Organizer: Gizem

* Sallie, Gizem: Ethics

* Stephanie: Social Policy Analysis Introduction

* Mark: Qualitative Research

* Dave: Bayesian statistics

* Vicki: Visualization

* Josh: Statistical Analysis?

* Bianica: Agent-Based Modeling

DSPG Symposium (July 27th)

Draft Agenda (12pm-5pm)

Welcome & Introductions

Speaker: Sallie Keller, Director and Professor of Statistics, SDAL

Welcoming Remarks

Speaker: TBD – VT Leadership

Keynote Speakers:

Nancy Potok (confirmed)

Chief Statistician of the United States, Office of Management and Budget

David Yokum (confirmed)

Director, The Lab @ DC, Executive Office of the Mayor, Office of the City Administrator

- Break -

Speed Session:

DSPG Fellows promote their research posters and invite the audience to review their posters.

Poster Session & Networking Reception:

Participants review the posters and interact with the students; refreshments will be provided.

Field Trips

* need both substantive and fun outings

* meetups (Daniel)

* mock trial (Stephanie -- tickets to this are $20 for students)

* some seminar/event at NSF? (Stephanie?)

* volleyball (Gizem)

Suggestions?