Plans for DSPG 2018

- Scheduling

| Week | DSPG 2018 dates | VT Calendar |
| --- | --- | --- |
| Wk 1 - May 21-25 | DSPG Fellows start | VT Summer I Classes start on May 21 |
| Wk 2 - May 29-Jun 1 | DSPG Students start |  |
| Wk 3 - Jun 4-8 |  |  |
| Wk 4 - Jun 11-15 |  |  |
| Wk 5 - Jun 18-22 |  | VT Summer I Exams begin on June 29 |
| Wk 6 - Jun 25-29 | DSPG midterm presentations | VT Summer I Classed End on June 28 VT Summer I Exams end on June 30 |
| Break - Jul 2-6 |  | VT Summer II classes start on Jul 2 |
| Wk 7 - Jul 9-13 |  |  |
| Wk 8 - Jul 16-20 |  |  |
| Wk 9 - Jul 23-27 |  |  |
| Wk 10 - Jul 30-Aug 3 | JSM attendance |  |
| Wk 11 - Aug 6-10 | DSPG Student Final Week August 9th DSPG Symposium | VT Summer II Classed End on Aug 9 VT Summer II Exams end on Aug 11 |

- Staffing

- ~15 undergraduate students (as of today: 17 applicants (7 honors), 7 registered)

- DSPG Alumni: Eirik

- 5 fellows + 1 intern:

| Name | University | Degree | Background |
| --- | --- | --- | --- |
| Daniel Liden | Minnesota twin cities | MS Statistics | History & Philosophy |
| José Calderón | Claremont Grad Univ. | PhD Econ | Econ |
| Davon Woodard | VT | PhD Urban Planning | Public Policy + Psychology + Econ |
| Emily Sheen | Penn State | PhD Statistics | Math + Business Econ |
| Fanfang Lee | NYU | MS Statistics | Psychology |
| Devika Nair | American Univ. | MS Data Analytics | Neuroscience |

- SDAL faculty responsibilities

- Lead projects and write-up descriptions

- Arrange interaction with project sponsors

- Faculty presence & attendance to project meetings

    - Weekly kick-off and wrap-up meetings

- Student performance monitoring and early action

- Mentorship

- Trainings/Brownbags

- Arrange interesting site visits and activities

- Symposium

- Save the date: August 9th

- Attendance important + Outreach

- Keynote speakers – TBD

- PROJECTS

- Potential Project List

| Project | Sponsor | Funding situation | Lead | SDAL Team | Size |
| --- | --- | --- | --- | --- | --- |
| Regional Planning in Roanoke | Roanoke Valley Alleghany Regional Commission | GFURR |  |  |  |
| Enrollment of Underserved and Underrepresented Minority Students | VT Office of Academic Decision Support | Vice Provost (Ken Smith) |  |  |  |
| STEM Pathways | NCSES | USDA / NSF |  |  |  |
| Business Innovation | NCSES | USDA / NSF |  |  |  |
| Open Source Software | NCSES | USDA / NSF |  |  |  |
| Army Installation Explorer/Dashboard | Army Research Institute (ARI) | ARI |  |  |  |
| Economic and Social Impact of Arlington Restaurant Initiative | ACPD | VT Center for Peace Studies and Violence Prevention |  |  |  |
| Data Linkage | AC DHS |  |  |  |  |
| Affordable Housing | Arlington Partnership for Affordable Housing (APAH) |  |  |  |  |
| Fairfax? | Fairfax |  |  |  |  |
| Foster – Child Allocation? | UMFS |  |  |  |  |
| VLDS (Tod)? | VLDS |  |  |  |  |
| Early Childhood Information Decision System (ECIDS) ? | VCEF | (VCEF) |  |  |  |
| VDOE/VDH (Derek)? | VDH? |  |  |  |  |
| VDH (OEMS)? | VDH | (VDH) |  |  |  |
| Conflict in Latin America / Food-Energy? | NGA |  |  |  |  |

- Summer Research Staff: Stephanie, Aaron, Gizem, Vicki, Bianica, Josh, Brian, Ian

- Please complete a one-page document addressing the elements below (and will be sent out in an email) to describe each project(s) that you volunteer to lead. Please send completed descriptions by May 11th to us. These descriptions will help us with the design (e.g., allocation of fellows/students.) and help the fellows and students with their project choices.

- Projects should be scaled to a level where a team of 2–3 students can make significant progress over 10 weeks, with good likelihood of arriving at some definitive result. Students will participate on at least 2 projects during the course of the summer program.

- Final list of projects (the lead, SDAL team, and DSPG team size), determined by Sallie in consultation with us, will be presented during an all SDAL meeting TBD. Decisions will be based on project scope and alignment to programmatic (funded projects and program development) priorities and skill sets of students.

- Leads will also prepare (2-3) slides and present to the students when they arrive.

- TRAININGS

Rough Plan:

| Week 1 | - Fellows and Faculty - Git and Rstudio |  |
| --- | --- | --- |
| Weeks 2-4 | - Research Skills | - IRB and Ethics (Sallie and Gizem) - Data Science Process - Library Resources (Library & Vicki) - Literature Reviews (Vicki) |
|  | - Data Skills | - Data Project Organization - Data Management - R - SQL - Data Objects - Git - Data Acquisition - Scraping - APIs (CENSUS, FCC, USDA, others) - Regex - Databases - Data Analysis - Exploration - Modeling - Machine Learning - Data Presentation - Data Visualization - Plotting/Mapping - Graphic Standards & Color Theory (Vicki) - Markdown, Tex - Shiny |
| Weeks 4-8 | - Professional Skills | - Media Speaking - Media Writing (Sage) |
|  | - Advanced Topic Seminars | - Agent-Based Modeling - Others? |

- SEMINARS/BROWNBAGS

* Stephanie: Social Policy Analysis Introduction

* Miron: Randomized Control Trials

* Dave: Bayesian statistics

* Others: TBD

PROJECT ELEMENTS

- Project Sponsor/Collaborator (e.g., Arlington County Police Department). List the sponsoring organization and the individual point-of-contact(s) & titles.

- Proposed SDAL Team (i.e., faculty/postdoc), and external (non-SDAL) colleagues, if any.

- Project Description. Provide a more detailed description. This should not be lengthy, but it should address each of the following elements.

- Project Summary. Give a concise (1–2 sentence) summary of the DSPG project (i.e., the “question” or “challenge”). It could be a concise question (“How can our animal shelter adopt out more dogs?” “How should we best deploy medical workers to reach the vulnerable population?”) or an open-ended challenge (“Develop an algorithm to advise parents how to choose among camping programs according to personal preferences, income, and location.”)

- If this is part of a larger SDAL project, provide a 1-2 sentence of the overall project and the link between the two.

- Elaborate upon the question/challenge of the summer project. Delineate the scope as much as possible.

- Why is the project important to the sponsor/collaborator?

- Why is the project important to SDAL (e.g., potential funding)?

- What (if any) prior work has been done on this project? Are there existing data sets or papers/models that you will provide to the students?

- What are students expected to do in steps (e.g., literature review, data discovery, modeling)?

- What is the minimum number of students/fellows requested? Do the students require special skills (e.g., facility with a specific programming language or software platform; background in biology, economics, webscraping, etc.)?

- Expectations. Describe what you expect from a successful project. Beyond the final project report and presentation, do you seek any other deliverable (e.g., annotated bibliography, draft paper)