DSPG Project – ARI – Summer 2023

Research questions:

- Extracting key developmental assignments from ARI Documents

- Documents as Data & Key ethical considerations

  - Contributing to open-source resources on ethical topics

  - Comparing language modeling algorithms (BERT and GPT2)

Potential literature review:

- GAO Reports about Recruiting and Retention

“Methods in Documents as Data”

Part 1. Data Extraction

- Key methods questions:

  - How do we extract data from documents?

  - What considerations are to be made about the scope of data?

- Key research questions:

  - What positions/assignments are the same across branches and functional areas?

  - What positions/assignments are unique to specific branches and functional areas?

  - What behaviors and skills (if any) are associated with these positions/assignments?

- Goal: Build and analyze a dataset of key developmental positions and broadening assignments.

Part 2. Modeling Documents as Data

- Key methods questions:

  - How do we make the best decisions about modeling documents as data? What considerations should be made in regards to model selection?

  - How do we contextualize a corpus within a large language model? How do we contextualize the results of NLP modeling, specifically analysis with LLMs?

  - Can a topic-specific corpus be modeled effectively using LLMs?

- Key research questions:

  - What prescriptive and descriptive behaviors are associated with Soldier and unit performance and related concepts (e.g., cohesion, teamwork, leadership)?

  - How is performance broadly connected to psychosocial characteristics?

  - Are these behaviors connected to any psychosocial characteristics?

  - Can these performance findings be connected back to our dataset of key developmental positions and broadening assignments?

- Goal: Compare the output of two modeling strategies, e.g., where is there convergence/divergence in the identification of performance-related behaviors and their connections to psychosocial traits?

- Goal: Contribute our findings to open-source materials.

Requirements: Getting BERT/GPT on machines, might require Python and R

Consideration: Technical requirements of students

What about a way to validate what we’re doing? How might we pull out the actual differences (counts), actually comparing to the definitions document

We’ve made contact with the Hugging Face Machine Learning Librarian!

|  | Students | Staff |
| --- | --- | --- |
| Lane 1 Lane 2 Deliverable |  | Prep: Skylar document code, develop plan for DSPG students, codify technical requirements |
| Week 1 5/29 – 6/2 (5/29 Memorial Day) | - Receive project assignments - Read background material | - Joanna: Give introduction to the documents - All: Make sure materials/tools are accessible |
| Week 2 6/5 – 6/9 (6/8 – 6/9 Joanna out) | - Data discovery for master list of assignments - Explore methods for extracting data from documents - Select and pursue a method, more than one method | - Joel: Give Introduction to the ARI projects |
| Week 3 6/12 – 6/16 | - Continue extracting data - Begin analyzing data per research questions | - Potentially leverage analysis of position data in the cPDE |
| Week 4 6/19 – 6/23 (6/19 Juneteenth) | - Finish any remaining data extraction - Continue analysis - Familiarize with BERT analysis | - Potentially leverage analysis of position data in the cPDE |
| Week 5 6/26 – 6/30 | - Cushion time - Prepare presentation materials - Familiarize with BERT analysis - Make sure BERT is installed by now 6/30 Midterm presentation - Draft/Outline Methodspace (sample due to Rachel) | - Potentially leverage analysis of position data in the cPDE |
| Week 6 7/3-7/7 (7/4 Independence Day) | - Analyze documents with GPT2 - Read up on algorithms, training data - Outline project website | - Potentially leverage analysis of position data in the cPDE |
| Week 7 7/10 – 7/14 | - Analyze documents with GPT2 - Compare to the BERT analysis - Read up on algorithms, training data - Work on Methodspace article (writing session) - Draft project website (wait for Joanna’s template) 7/13 Methodspace article draft | - Potentially leverage analysis of position data in the cPDE |
| Week 8 7/17 – 7/21 | - Finish analysis, comparison - Contribute to open source materials - Potentially revisit to pair analysis with PDE results 7/21 Project website draft | - Potentially leverage analysis of position data in the cPDE |
| Week 9 7/24 – 7/28 | - Cushion time - Prepare presentation, other final materials - Potentially revisit to pair analysis with PDE results | - Potentially leverage analysis of position data in the cPDE |
| Week 10 7/31 – 8/4 | - Finish preparing presentation, other final materials 8/2 Final project website 8/2 Final Methodspace article 8/3 DSPG Symposium (presentation? Poster) |  |