DSPG Summer Project – Impact of Broadband Programs

Project Sponsor

- John Pender, USDA Economic Research Service

SDAD team

- Joshua Goldstein

- Neil Kattampalil

- Leonel Siwe

Project Goal

USDA would like to know whether broadband development has an effect on broadband adoption and rural prosperity, as measured by changes in property values and quality of life indicators in rural communities. We will examine the impact of programs that develop broadband infrastructure, with a focus on grants and loans from the USDA Rural Utility Service (RUS). Students will use Ookla speedtest data to assess the impact of the Community Connect and ReConnect broadband programs. We will clean and geocode BlackKnight housing data in order to link household information to broadband subscription speeds.

Student Involvement

- Clean and geocode BlackKnight housing and tax assessment data.

- Link housing data to RUS broadband programs.

- Link Ookla speedtest data to RUS broadband programs.

- Implement statistical methods to assess broadband program impacts.

Expectations / Deliverables

- Data products:

  - Ookla data linked to ReConnect programs

  - Cleaned BlackKnight assessment data linked to ReConnect programs

- EDA + Midterm presentation

- Final poster and presentation

- Project documentation

Timeline

Week 1: 5/30-6/2

- Introductions and project teams

- Project background review

Week 2: 6/5-6/9

- Obtain and review daata; BK housing data and Ookla data

Week 3: 6/12-6/16

- Geocoding BK data

Week 4: 6/19-6/23

- Linking and cleaning data

Week 5: 6/26-6/30

- Midterm presentation

Week 6, 7, 8: 7/3-7/21

- Implementing statistical models to measure impact of RUS programs:

  - Broadband adoption using Ookla

  - Poperty values using BlackKnight

Week 9: 7/24-7/28

- Draft of final presentation

Week 10: 7/31-8/4

- Documentation

- Final presentation